## Test Plan
Chronotimer 1009 Test Plan
Test Plan ID | 1
Author | David
Features being tested
1 | IND Race
Resources requried: | ChronoTimer Project
Testers: | David
Scheduling: | 2018-05-05
Data/Test files: | Test1.txt
Initial state: | System is off with no queued runners or channels on.
Components: | Individual race, Connect command
Test Plan ID | 2
Author | Zac
Features being tested
2 | PARIND Race
Resources requried: | ChronoTimer Project
Testers: | Zac
Scheduling: | 2018-05-05
Data/Test files: | Test2.txt
Initial state: | System is off with no queued runners or channels on.
Components: | PARIND race, Event, Triggers
Test Plan ID | 3
Author | Ryan
Features being tested
3 | GRP Race
Resources requried: | ChronoTimer Project
Testers: | Ryan
Scheduling: | 2018-05-05
Data/Test files: | Test3.txt
Initial state: | System is off with no queued runners or channels on.
Components: | Group race, json, Export command
Test Plan ID | 4
Author | Ryan/Zac
Features being tested
4 | PARGRP Race
Resources requried: | ChronoTimer Project
Testers: | Mariah
Scheduling: | 2018-05-05
Data/Test files: | Test4.txt
Initial state: | System is off with no queued runners or channels on.
Components: | PARGRP race, server display
Test Plan ID | 5
Author | Zac
Features being tested
4 | SWAP Command
Resources requried: | ChronoTimer Project
Testers: | Zac
Scheduling: | 2018-05-09
Data/Test files: | Test4.txt
Initial state: | System is off with no queued runners or channels on.
Components: | SWAP command, DNF, all racetypes

## Test Cases Test Plan ID 1
Test Case ID | Test Case Description | Input values | Expected Output | Actual | Pass/Fail | Author | Tester
TC01.01 | Power On | POWER | Chronotimer on | power on | pass | David
TC01.02 | Connect Sensors | CONN GATE 1 | Sensor connected | ch1 connected to gate sensor | pass
TC01.03 | ... | CONN EYE 2 | Sensor connected | ch2 connected to eye sensor | pass
TC01.04 | Sensor already connected | CONN EYE 1 | Error chan 1 already connected | ch1 already connected | pass
TC01.05 | Ready channels | TOG 1 | Chan 1 ready | ch1 ready | pass
TC01.06 | ... | TOG 2 | Chan 2 ready | ch2 ready | pass
TC01.07 | Invalid start | TRIG 1 | No runners queued | no racers started. None in the queue | pass
TC01.08 | ... | TRIG 2 | No runners queued | no racers finished. None in the queue | pass
TC01.09 | Queue runners | NUM 123 | 123 ready to start | racer 123 in the queue | pass
TC01.10 | ... | NUM 234 | 234 ready to start | racer 234 in the queue | pass
TC01.11 | Begin running | TRIG 1 | 123 starts running | racer 123 running | pass
TC01.12 | ... | TRIG 1 | 234 starts running | racer 234 running | pass
TC01.13 | No runners queued | TRIG 1 | Error no runners are queued | no racers started. None in the queue | pass
TC01.14 | Finish race | TRIG 2 | 123 finishes | racer 123 ends | pass
TC01.15 | ... | TRIG 2 | 234 finishes | racer 234 ends | pass
TC01.16 | Nobody running | TRIG 2 | Error nobody running | no racers finished. None in the queue | pass
TC01.17 | End run | ENDRUN | Run ends, displays correct times | times of racers are displayed | pass
TC01.18 | Print results | PRINT | Publish results | times of racers are displayed to console | pass

## Test Cases Test Plan ID 2
Test Case ID | Test Case Description | Input values | Expected Output | Actual | Pass/Fail | Author | Tester
TC02.01 | Test EVENT Race PARIND | Turning on the system & setting event to PARIND. POWER EVENT PARIND | racetype = PARIND | r1 racertype = PARIND | pass | Zac | Zac
TC02.02 | Test two racers | racers in queue to running to finish. POWER EVENT PARIND TOG 1 TOG 2 TOG 3 TOG 4 NUM 1 NUM 2 TRIG 1 TRIG 3 TRIG 2 TRIG 4 PRINT ENDRUN | racers finish time. racer in finish queue. | finished racers should be printed out and sent to the server. | pass | Zac | Zac
TC02.03 | Test with no racers queued | start event with no racers queued up. POWER EVENT PARIND TOG 1 TOG 2 TOG 3 TOG 4 TRIG 1 | should not allow race to start "There are no racers queued to start." | no racers started. None in the queue | pass | Zac | Zac
TC02.04 | Test channel 1,2,3, and 4 | try to start event with channel 2 or 4 POWER EVENT PARIND TOG 1 TOG 2 TOG 3 TOG 4 NUM 1 NUM 2 TRIG 2 TRIG 4 | will not queue a racer unless it's on channel 1 or 3. "There are no racers currently running." | no racers finished. None in the queue | pass | Zac | Zac
TC02.05 | Test finish event | after two runners have started and niether have finished, then if either channel 2 or 4 is triggered it will cause the first runner to finish. POWER EVENT PARIND TOG 1 TOG 2 TOG 3 TOG 4 NUM 1 NUM 2 TRIG 1 TRIG 3 TRIG 4 TRIG 2 PRINT ENDRUN | racer 1 will finish on trigger 4 and racer 2 will finish on trigger 2 | finished racers should be printed out and sent to the server. | pass | Zac | Zac

## Test Cases Test Plan ID 3
Test Case ID | Test Case Description | Input values | Expected Output | Actual | Pass/Fail | Author | Tester
TC03.01 | Event from IND to GRP | POWER EVENT IND EVENT GRP | racetype = GRP | racetype = GRP | pass | Ryan Fox | Ryan Fox
TC03.02 | IND to GRP, with racers | POWER EVENT IND NUM 1 NUM 2 EVENT GRP | racetype = GRP | racetype = GRP | pass | Ryan Fox | Ryan Fox
TC03.03 | Creating a json then creating a race from that json | POWER EVENT GRP NUM 1 NUM 2 PRINT RESET EXPORT SETRACE RUN1.txt | race = oldrace | race is set to json race | pass | Ryan Fox | Ryan Fox
TC03.04 | Testing the finish of GRP Race | POWER EVENT GRP NUM 1 NUM 2 TOG 1 TOG 2 TRIG 1 TRIG 2 2 EXPORT | json text file | export partially completed race | pass | Ryan Fox | Ryan Fox
TC03.05 | Testing sample race from json | POWER EVENT GRP NUM 111 NUM 222 NUM 333 NUM 444 EXPORT SETRACE RUN1.txt TOG 1 TOG 2 TRIG 1 TRIG 2 111 TRIG 2 333 TRIG 2 444 | racer 111,333, and 444 will finish. Racer 222 DNF | finished race completed and displayed on server | pass | Ryan Fox | Ryan Fox

## Test Cases Test Plan ID 4
Test Case ID | Test Case Description | Input values | Expected Output | Actual | Pass/Fail | Author | Tester
TC04.01 | Test that less than 8 racers start | POWER EVENT PARGRP TOG 1 TOG 2 TOG 3 TOG 4 TOG 5 TOG 6 TOG 7 TOG 8 NUM 1 NUM 2 NUM 3 NUM 4 NUM 5 NUM 6 NUM 7 NUM 8 NUM 9 TRIG 1 | Racer 9 will not be in the running queue | 8 racers start running, racer 9 still in the queue | pass | Z/R | Mariah
TC04.02 | Test that racers are set to one channel for finishes | POWER EVENT PARGRP TOG 1 TOG 2 TOG 3 TOG 4 TOG 5 NUM 1 NUM 2 NUM 3 NUM 4 NUM 5 TRIG 1 TRIG 3 PRINT ENDRUN | Racer 3 would finish other racers DNF | racer 3 finishes the rest DNF | pass | Z/R | Mariah
TC04.03 | Testing Channels | POWER EVENT PARGRP TOG 1 TOG 2 TOG 3 TOG 4 TOG 5 NUM 1 NUM 2 NUM 3 NUM 4 NUM 5 TRIG 1 TRIG 6 | Triggering 6 with only five racers will not finish a racers | nothing happens. All racers still running | pass | Z/R | Mariah
TC04.04 | Testing Channel 1 | POWER EVENT PARGRP TOG 1 TOG 2 TOG 3 TOG 4 TOG 5 NUM 1 NUM 2 NUM 3 NUM 4 NUM 5 TRIG 1 TRIG 1 PRINT ENDRUN | Race will start and then racer 1 will finish | racer 1 finishes. The rest DNF | pass | Z/R | Mariah
TC04.05 | Testing a sample run with 8 runners | POWER EVENT PARGRP TOG 1 TOG 2 TOG 3 TOG 4 TOG 5 TOG 6 TOG 7 TOG 8 NUM 1 NUM 2 NUM 3 NUM 4 NUM 5 NUM 6 NUM 7 NUM 8 TRIG 1 TRIG 4 TRIG 3 TRIG 1 TRIG 2 TRIG 8 TRIG 6 | all runners should finish and the running queue should be empty | all racers finish and results are printed to the console and displayed to the server | pass | Z/R | Mariah
TRIG 5 TRIG 7 PRINT ENDRUN

## Test Cases Test Plan ID 5
Test Case ID | Test Case Description | Input values | Expected Output | Actual | Pass/Fail | Author | Tester
TC05.01 | Testing swap on IND race | POWER EVENT IND TOG 1 TOG 2 NUM 1 NUM 2 TRIG 1 TRIG 1 SWAP TRIG 2 TRIG 2 PRINT RESET | racer 2 will finish first then racer 1 will finish | racer 2 finishes on first trig 2 and racer 1 finishes on second trig 2 | pass | Zac | Zac
TC05.02 | Testing swap on PARIND race | POWER EVENT PARIND TOG 1 TOG 2 TOG 3 TOG 4 NUM 1 NUM 2 TRIG 1 TRIG 3 SWAP TRIG 2 TRIG 4 PRINT RESET | racer 2 will finish first then racer 1 will finish | racer 2 finishes on trig 2 and racer 1 finishes on trig 4 | pass | Zac | Zac
TC05.03 | Testing swap on PARIND race with DNF | POWER EVENT PARIND TOG 1 TOG 2 TOG 3 TOG 4 NUM 1 NUM 2 TRIG 1 TRIG 3 SWAP DNF SWAP TRIG 2 PRINT RESET | racer 2 will have a DNF and racer 1 will finish | racer 2 has DNF and racer 1 finishes on trig 2 | pass | Zac | Zac
TC05.04 | Testing swap on GRP race | POWER EVENT GRP TOG 1 TOG 2 NUM 1 NUM 2 NUM 3 NUM 4 NUM 5 TRIG 1 SWAP TRIG 2 2 SWAP TRIG 2 3 TRIG 2 1 PRINT ENDRUN RESET | racers still swap but trig will dictate which racer finishes in what order | racer 2 finishes first then racer 3 finishes and then racer 1 finishes | pass | Zac | Zac
TC05.05 | Testing swap on PARGRP race | POWER EVENT PARGRP TOG 1 TOG 2 TOG 3 TOG 4 NUM 1 NUM 2 NUM 3 NUM 4 TRIG 1 SWAP TRIG 1 TRIG 4 TRIG 2 TRIG 3 PRINT ENDRUN RESET | swap wont work on PARGRP. Don’t want racers to switch channels | swap didn’t change racers connection to their specific channel | pass | Zac | Zac